## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2025-02-22 | Cecilia | P2 | Resolved | Cecilia | The current walls are drawn as half tiles but the collision box is for the full tile. This causes any collision to look like it's stopping short of the wall. | Player should stop at wall | Player stops just before wall | Walk into a wall with the player.
2 | 2025-02-22 | Elton | P3 | Resolved |  | Sword hitboxes are wrong, and are much more generous than they should be | Sword hitbox should be roughly the size of the sword | Sword hitbox creates a square with the bottom-left as the hilt and top-right as the blade. Every pixel in the square counts for the collision. | Swing the sword such that it doesn't visibly hit but is close to hitting
4 | 2025-02-23 | Elton | P3 | Open |  | Placeholder player attack animations don't make sense. This should be fixed when we finalize our sprites. | Attack animation does not contain a slash | Attack animation contains a slash | Do an attack
5 | 2025-02-22 | Stephane | P4 | resolved | Stephane | (FEATURE REMOVED) Enemy-enemy collisions cause unpredictable movement | Enemies attempting to move into the same space do not overlap | Enemies will semi-regularly teleport around or disappear off the map when moving while in contact or colliding with multiple entities. | DISABLED IN M1 BUILD. Otherwise, maneuver so that 2 or more enemies come into contact, and move until weird things happen.
6 | 2025-02-23 | Stephane | P4 | won't fix |  | Enemies get stuck on corners | Enemies will navigate around corners to follow the player | Enemies will sometimes stop moving when trying to get around a corner | Get an enemy to try following you around a corner.
7 | 2025-02-23 | Stephane | P4 | won't fix |  | Enemies move when window is moved | Enemy behavior does not change when the window is clicked or moved. | Enemies will move away from each other when the window is moved or clicked | Move the window. | The "lag" from when you move the window causes enemies to move in their current direction as a result of our physics system, overhauling the physics system is not on the table right now
8 | 2025-03-05 | Cecilia | P4 | resolved | Cecilia | Grid lines appear in the map due to the GPU sampling other tiles when scaling up textures. Using a tile extruder may be a possible solution. | Tile should connect together seamlessly | Tiles have a thin "grid line" in between them | Load up the game.
9 | 2025-03-09 | Emma | P4 | resolved | Emma | When I revisit the tutorial, the player can't exit the map to skip | Player can exit the map to skip at anytime | Player can exit the map during tutorial on the first attemp, but after revising the tutorial player can't exit | Revisit the tutorial
10 | 2025-03-09 | Emma | P4 | resolved | Emma | When I revisit the tutorial, it starts with three enemeis. | There should be no enemeis at the beginning of the tutorial | When I revisit the tutorial, it starts with three enemeis. | Revisit the tutorial
11 | 2025-03-09 | Elton | P4 | resolved | Emma | Clicking on the screen then going to the tutorial causes a swing to occur immediately | There should be no swing | There is a swing | Click on the menu screen then go to the tutorial (maybe also normal level)
12 | 2025-03-09 | Elton | P4 | Resolved | Emma | The ranged step of the tutorial does not proceed until after the enemy is dead and right click is pressed. | The tutorial should proceed after the enemy dies from the projectile | The tutorial is stuck on the ranged step until right click is pressed after the enemy is dead | Go through the tutorial until the ranged attack step
13 | 2025-03-09 | Elton | P3 | Resolved | Elton | The projectiles sometimes doesn't seem to hit the enemy? | The projectile should hit the enemy if it collides | Sometimes the projectile doesn't look like it actually hits the enemy, need to investigate what exactly is happening here | Try spamming ranged attacks on enemies. Sometimes they will not have the hit feedback
14 | 2025-03-09 | Emma | P4 | resolved | Emma | The melee and ranged step of the tutorial can use either attacks to kill the enemy. | The melee step should only allow melee attack, and ranged step should only allow ranged attack. | Both melee and ranged attacks can be used to kill the enemy for both steps - player can go to the next step without using the attack they are supposed to use | Go through both melee and ranged attack steps and try both attacks
15 | 2025-03-09 | Elton | P4 | resolved | Elton | Item spawns in tutorial after killing first enemy, it's then removed but flashes for a frame | The item should not spawn at all | Item spawns and is deleted immediately after | Go through the tutorial and kill the first enemy in the melee step
16 | 2025-03-09 | Cecilia | P4 | won't fix |  | Gridlines appear when you enter a new map and stop moving. But they disappear when you move. | There should be no gridlines at all | There are gridlines when entering a new map | Enter another map and stop moving.
17 | 2025-03-23 | Cecilia | P4 | won't fix |  | Sword slash sound effect is played once when left clicking in the main menu | There should be no sound effect played when left-clicking on the main menu | Sound effect is played | After game opens, left click anywhere on the screen.
18 | 2025-03-23 | Cecilia | P2 | resolved |  | Background music fails to load | There should be background music playing | There is no background music | Run the game
19 | 2025-03-23 | Cecilia | P2 | resolved |  | Game crashes sometimes when using a projectile attack on enemies. | Game should not be crashing | Game is crashing | Spam ranged attacks at enemies. Every so often it will fail.
20 | 2025-03-23 | Cecilia | P4 | resolved |  | When clicking on save in the pause menu, the screen darkening flips. | Clicking on the save button in the pause menu should not be lightening or darkening the screen | The save button lightens/darkens the screen | Start playing the game and hit pause. Select the save button.
21 | 2025-03-23 | Cecilia | P4 | resolved | cecilia | When entering the game again after dying, items spawn in the room. | You should be spawning in an empty room with no items | You spawn into a room with items. | Die in the game and respawn
22 | 2025-04-06 | Stephane | P3 | wont' fix | stephane | Boss ranged attack angles incorrect | When boss performs a ranged attack, all projectiles should fan out towards the player | Some projectiles will head off in other directions. | Provoke the boss into performing a ranged attack

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected, should fix in the next sprint
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release